December 2011 Report

| To : | Eseta Nonu-Reid |
| --- | --- |
| From : | Project Consultant, Deirdre Mulligan |
| Date : | 8th December 2011 |
| Re: | MRN CAMHS Project |

Recommendations

- That the Manager  receives the information

- That the Manager note any issues pertaining to these activities or the information provided that she would wish to discuss with the Project Manager.

Activity: September /December  2011

1. Scoping the project

The project scope has been signed off and agreed by the Project Sponsors.

2. Technical Advisory Group

An inaugural teleconference with the MRN CAMHS Technical Advisory Group was held on the 2nd December. Although a number of the members were unable to participate, it was useful to hold this in advance of Christmas to make sure we have an agreed process to move forward on in the New Year. The Project Consultant will be making contact with individual members who could not make the teleconference to ensure everyone is appraised of the project and agreed approach.

Noted that ADHB Funder representation is still to be sought, and we do not have representation from Taranaki DHB. The Project Consultant will follow this up with the Project Sponsor.

The project scope was discussed and will be dates will be amended based on feedback and agreement from the group on what is realistic and achievable. A terms of Reference will be drafted to guide the activity of the Technical Advisory group.

Proposed dated have been circulated for 2 teleconferences (17th Feb & 16th March) and a face to face workshop planned in Hamilton on either 27th March or 3rd April.

3. Data sources and Data Collection

There have been brief discussions with the TAG about what information would be helpful with regards to Midland DHBs access and utilisation of the CFU. A follow-up discussion has occurred with Sarah Wallbank, Service Manager at ADHB, and we will be looking to table a summary at the February teleconference.

## Challenges

DHBs continue to be working with a sense of urgency on a number of matters such as requirements for the annual planning cycle. Given the limited capacity of key TAG members to be able to meet/attend at the dates proposed, the most pragmatic way forward is for the project consultant to actively communicate with members outside of standard meeting times if they are unable to attend.

## Any queries?

Should there be any queries about this report, please follow up with the project consultant.

Attachments:

- Teleconference Minutes 2nd Dec 2011

|  | Minutes of Midland CAMHS Project 9.30am, 2nd December 2011 Teleconference number dial in 083033 and Pin No: 531483 |  |
| --- | --- | --- |

Present: Arran Culver, Jik Loy, Sue Sundheim.

Apologies: Sue Mackersey, Katherine Fell, Sarah Wallbank, Pauline Mckay, Leah Andrews, Eseta Nonu-Reid, Belinda Walker.

| No. | Topic | Discussion Points | Planned Action | By |
| --- | --- | --- | --- | --- |
| 1.0 | Whakatau / Welcome | - Deirdre welcomed members - Noted apologies |  |  |
| 2.0 | AGENDA ITEMS |  |  |  |
| 2.1 | Previous Minutes | - Nil |  |  |
| 2.2 | Matters arising | - Nil |  |  |
| 2.3 | Project Overview | - Tabled and discussed. Noted there has been some slippage in the timeframes and the key purpose of the day was to engage with the Technical Advisory Group (TAG) before Christmas to agree a way forward/dates for the New Year - Noted – we don’t have Taranaki Representation & ADHB Funder - There will be the opportunity to talk with other members of TAG to have a phone discussion as well so everyone is up to date with the intent of the project - Queries as to whether this project was a result of discussions at the Midland CAMHS meeting earlier in the year when there were concerns expressed about consistency in accessing CFU services - TAG members would like to get a copy of the previous minutes - Noted that access has improved to CFU, but a formalised Service Level Agreement (SLA) would be helpful. - A number of processes have been developed (e.g Waikato access to on-call CFU psychiatrist out of hours), and this protocol is in draft currently, awaiting formal internal sign off. - Useful to feed these developments into future discussions - Requested TAG consider what information they have that will assist in developing the SLA for discussion at the next meeting - TOR to be drafted for the group | Resend updated word version with revised dates and updated comments Follow-up with Sponsor Circulate when sourced Agenda item next meeting Draft TOR to be circulated as an agenda item in advance of the next meeting | Deirdre Deirdre Deirdre All Deirdre |
| 2.4 | General Discussion | - Other areas that need to be reflected in the SLA - Transport issues, especially where there are safety concerns – note this is resource heavy - Forensic clients – especially where there are delays in transfers and clients are detained in police cells - Noted that a recent funding announcement was made to improve early intervention and treatment services for youth offenders - Need to gain better access to data/utilisation – thought this information sits with P&F, not getting to DHBs at a service level | Sue to forward link to include in the minutes http://www.beehive.govt.nz/release/new-youth-forensic-mental-health-services-announced | Sue |
| 2.5 | Future Meetings | - Expected time commitment would be 2 teleconferences and one face to face meeting - Preferred dates – 3rd Friday of the Month (9.30 – 11am) - Discussed a face to face workshop in Hamilton – tentatively Tues 6th March (10 – 2.30) - POST NOTE: This would not allow for 2 teleconferences in advance of the workshop – propose either Tues 27th March or Tues 3rd April | Deirdre/Akatu to confirm dates and send outlook invitations | Deirdre |
| 3.0 | Meeting Close | Thanks to those who had attended. Others to advise Deirdre of a time that would suit them to have a phone conversation as follow-up. |  |  |